## Team List
Team List
No | ID | Surname | Name
1 | 293981 | Simoni | Gabriele
2 | 293988 | Dalgın | Hüdalfa Bera
3 | 288599 | Shirasaki | Nozomi Malke
4 | 293864 | Parra Mejido | Erik
5 | 293891 | Prétet | Cédric Minh

## Tasks Tracker
Tasks Tracker
No | State | Name | Artifact | Duration | Start | Finish | Predecessors | Assignement
[8 empty] | No | Name
1 | Done | Make Gantt graph | schedule.pdf | 5 | 2025-10-08 15:15 | 2025-10-13 15:15 |  | 1 | Simoni
2 | Done | Compile team list | team_list.pdf | 5 | 2025-10-08 15:15 | 2025-10-13 15:15 |  | 1 | Simoni
3 | Done | Choose title | title.pdf | 5 | 2025-10-08 15:15 | 2025-10-13 15:15 |  | 1 | Simoni
4 | Done | Define business goals | business_goals.pdf | 5 | 2025-10-08 15:15 | 2025-10-13 15:15 |  | 4 | Parra Mejido
5 | Done | Write domain description | domain.pdf | 5 | 2025-10-08 15:15 | 2025-10-13 15:15 |  | 3 | Shirasaki
6 | Done | Identifying external stakeholders | stakeholders.pdf | 5 | 2025-10-08 15:15 | 2025-10-13 15:15 |  | 2 | Dalgın
7 | Done | Identifying alternative solutions | solutions.pdf | 5 | 2025-10-15 15:15 | 2025-10-20 15:15 |  | 5 | Prétet
8 | Done | Identify application context | app_context.pdf | 5 | 2025-10-15 15:15 | 2025-10-20 15:15 |  | 3 | Shirasaki
9 | Done | Identify technological context |  | 5 | 2025-10-15 15:15 | 2025-10-20 15:15 |  | 3 | Shirasaki
10 | Done | Identify organisational context |  | 5 | 2025-10-15 15:15 | 2025-10-20 15:15 |  | 1 | Simoni
11 | Done | Identify legal context |  | 5 | 2025-10-15 15:15 | 2025-10-20 15:15 |  | 2 | Dalgın
12 | Done | Define technologies used | technologies.pdf | 5 | 2025-10-15 15:15 | 2025-10-20 15:15 |  | 1 | Simoni
13 | To-do | Update business goals | [5 empty] | 0 | unassigned
14 | To-do | Choose documentation tool | [5 empty] | 0 | unassigned

## Weeks List
Weeks List
No | Class | Deadline
1 | 2025-10-08 15:15
2 | 2025-10-15 15:15 | 2025-10-13 15:15
3 | 2025-10-22 15:15 | 2025-10-20 15:15
4 | 2025-10-29 15:15 | 2025-10-27 15:15
5 | 2025-11-05 15:15 | 2025-11-03 15:15
6 | 2025-11-12 15:15 | 2025-11-10 15:15
7 | 2025-11-19 15:15 | 2025-11-17 15:15
8 | 2025-11-26 15:15 | 2025-11-24 15:15
9 | 2025-12-03 15:15 | 2025-12-01 15:15
10 | 2025-12-10 15:15 | 2025-12-08 15:15
11 | 2025-12-17 15:15 | 2025-12-15 15:15
holiday | 2025-12-24 15:15 | 2025-12-22 15:15
holiday | 2025-12-31 15:15 | 2025-12-29 15:15
12 | 2026-01-07 15:15 | 2026-01-05 15:15
13 | 2026-01-08 15:15 | 2026-01-06 15:15
14 | 2026-01-09 15:15 | 2026-01-07 15:15
15 | 2026-01-10 15:15 | 2026-01-08 15:15
16 | 2026-01-11 15:15 | 2026-01-09 15:15
Formulas:
Deadline = [Class]-2